Phase 1:

Order all hardware for server test array

| Phase | Description of task | Status |
| --- | --- | --- |
| Start date | BASIC PROJECT START |  |
| 1 | Site survey of EarthLink COLO | Done |
| 1 | Receive signed P&S and check for project | Done |
| 1 - 11/05/14 | Oder all hardware for test server array | Done |
| 1 – 11/11/14 | Get OS software for main servers | In-Process |
| 1 | Get links to testing software and configuration files |  |
| 1 – 11/24/14 | Start receiving server equipment | In-Process |
|  | BENCH TEST ALL HARDWARE IN LOCAL LAB |  |
| 2 | Bench Test Main Servers in-house |  |
| 2 | Download Software and configuration files for Server Setup |  |
| 2 | Bench test TESTING servers (24) as they come in |  |
| 2 | Load OS and VM configuration files |  |
| 2 | Bench test both main servers |  |
| 2 | Configure COMTROL serial multiplexors and test |  |
| 2 | Configure HP 8 and 48 port switches |  |
| 2 | Configure APC PDU’s and test |  |
|  | INSTALL HARDWARE AT COLO |  |
| 3 | Move and Install PDU’s to COLO |  |
| 3 | Move and install network switches to COLO |  |
| 3 | Move tested main servers to COLO and Install |  |
| 3 | Move and test TESTING servers to COLO |  |
|  | ACCEPTANCE TESTING |  |
| 4 | Run Acceptance test on server array |  |
| 4 | Swap COMTROL cable and test server array |  |
| 4 | Simulate loss of internet connection |  |
| 4 | Simulate Power fail on 1 PDU |  |
| 4 | Simulate Power fail on both PDU’s |  |
| 5 | Download test scenario and run a complete platform test. |  |