Phase 1:

Order all hardware for server test array

| Phase |  | Description of task | Status |
| --- | --- | --- | --- |
| Start date | Stop Date | BASIC PROJECT START |  |
| 1 – 10/20/14 | 10/20/14 | Site survey of EarthLink COLO | Done |
| 1 – 10/20/14 | 10/28/14 | Receive signed P&S and check for project | Done |
| 1 - 11/05/14 | 11/08/14 | Order all hardware for test server array | Done |
| 1 – 11/08/14 | 12/31/14 | Work with Supplier to get equipment | Working |
| 1 – 11/13/14 | 11/14/14 | Get Debian OS Images | Done |
| 1 – 11/24/14 | 12/31/14 | Start to Receive hardware from supplier | On-Going |
| 1—11/24/14 | 12/03/14 | Develop Configuration plan and implement (See Startup Spread sheet – attached) | On-Going |
| 1 – 12/03/14 | 12/03/14?? | Receive Main Servers and Comtrol Multiplexor Components |  |
|  |  | BENCH TEST ALL HARDWARE IN LOCAL LAB |  |
| 2 – 12/02/14 | 12/04/14 | Prepare bench and Configure Switches for initial bench testing |  |
| 2 – 12/04/14 | 12/15/14 | Bench Test Main Servers in-house |  |
| 2 – 12/05/14 | 12/15/15 | Download Developed Software and configuration files for Server Setup |  |
| 2 – 12/10/14 | 12/31/14 | Bench test TESTING servers (24) as they come in |  |
| 2 – 12/10/14 | 12/20/14 | Load OS and VM configuration files |  |
| 2 – 12/10/14 | 12/20/14 | Bench test both configured main servers |  |
|  |  | CONFIGURATION TESTING |  |
| 2 – 12/15/14 | 12/20/14 | Configure COMTROL serial multiplexors and test |  |
| 2 – 12/15/14 | 12/20/14 | Configure HP 8 and 48 port switches for COLO operation |  |
| 2 – 12/18/14 | 12/20/14 | Configure APC PDU’s and test |  |
| 2 – 12/18/14 | 12/20/14 | Install 1or more Set of Test Servers and Run a test trial |  |
|  |  | INSTALL HARDWARE AT COLO (Allow for Christmas Holiday) |  |
| 3 – 12/22/14 | 12/30/14 | Move and Install PDU’s to COLO |  |
| 3 - 12/22/14 | 12/30/14 | Move and install network switches to COLO |  |
| 3 – 12/22/14 | 12/30/14 | Move tested main servers to COLO and Install |  |
| 3 – 12/22/14 | 12/30/14 | Move and test TESTING servers to COLO |  |
|  |  | ACCEPTANCE TESTING |  |
| 4 – 12/31/14 | 01/10/15 | Run Acceptance test on server array |  |
| Phase |  | Description of task | Status |
| Start Date | Stop Date |  |  |
| 4 – 01/02/15 | 01/10/15 | Swap COMTROL cable and test server array |  |
| 4 – 01/02/15 | 01/10/15 | Simulate loss of internet connection |  |
| 4 – 01/02/15 | 01/10/15 | Simulate Power fail on 1 PDU |  |
| 4 – 01/02/15 | 01/10/15 | Simulate Power fail on both PDU’s |  |
| 5 - 01/10/15 | 01/10/15 | Download test scenario and run a complete platform test. |  |